Organizing jamboree

Project outline

Version 0.2

# Work Breakdown Structure.

## Phases and deliverables:

## Time required to finish each task and dependences:

| TASKS: | TIME: (days) | DEPENDANCES: |
| --- | --- | --- |
| 1 Invitation scout teams |  |  |
| 1.1 Invite scout teams |  |  |
| 1.1.1 Collecting scout teams addresses | 2d |  |
| 1.1.2 Sending invitations | 1d | 1.1.1 |
| 1.1.3 Waiting for applications | 7d | 1.1.2 |
| 1.1.4 Creating list of teams and peoples | 1d | 1.1.3 |
| 2 Organizing place |  |  |
| 2.1 Assure place for jamboree |  |  |
| 2.1.1 Looking for available places | 2d |  |
| 2.1.2 Request for price | 1d | 2.1.1 |
| 2.1.3 Choosing the best offer | 1d | 2.1.2 |
| 2.2 Assure accommodation for the night |  |  |
| 2.2.1 Looking for available places | 2d |  |
| 2.2.2 Request for price | 1d | 2.2.1 |
| 2.2.3 Choosing the best offer | 1d | 2.2.2 |
| 3 Feeding |  | 1.1.4 |
| 3.1 Assure feeding |  |  |
| 3.1.1 finding a cook | 2d |  |
| 3.1.2 preparation of menu | 2h | 3.1.1 |
| 3.1.3 preparation list of ingredients | 2h | 3.1.2 |
| 3.1.4 buying ingredients | 1d | 1.1.4;3.1.3 |
| 3.1.5 preparing food | 2d | 3.1.4 |
| 4 Entertainments |  |  |
| 4.1 Assure entertainments |  |  |
| 4.1.1 preparation list of available entertainments | 4h |  |
| 4.1.2 choosing best from the list | 1h | 4.1.1 |
| 4.1.3 organizing equipment | 2d | 4.1.2 |
| 4.1.4 organizing entertainments | 3d | 4.1.3 |

## Gantt Chart

In file assignment_2_plezon.mpp

# Text boxes

4.1.3 organizing equipment

3.1.5 preparing food

1.1.4 creating list of teams and peoples

JAMBOREE

1.1 Invite scout teams

2.1 Assure place for jamboree

2.2. Assure accommodation for the night

3. Feeding

4. Entertainments

2. Organizing place

1. Invitation scout teams

3.1. Assure feeding

4.1. Assure entertainments

1.1.1 collecting scout teams addresses

1.1.2 - sending invitations

1.1.3 waiting for applications

2.1.1 looking for available places

2.1.2 request for price

2.1.3 choosing the best offer

2.2.1 looking for available places

2.2.2 request for price

2.2.3 choosing the best offer

3.1.1 finding a cook

3.1.2 preparation of menu

3.1.3 preparation list of ingredients

3.1.4 buying ingredients

4.1.1 preparation list of available entertainments

4.1.2 choosing the best from the list

4.1.4 organizing entertainments